## RAID
Type | ID | Title | Description | Theme | Category | Probability | Impact | Score | RAG | Response | Mitigations/Actions | Owner | Due/Target date | Status | Trend | Trigger/Threshold | Linked Tool/Process | Linked Change ID | Source/References | Last Updated
Risk | R-LGR-01 | LGR/Devolution changes alter SPA responsibilities mid‑process | Interim ToR in place; continuity and staffing assurances required; gateway plan to be reviewed. | C/G | Governance | 4 | 4 | 16 | Red | Reduce | Agree interim ToR; confirm staffing assurances; schedule gateway review | Programme Lead | 2026-03-15 | Open | Up | New governance decision expected Q2 | 3.3 ToR |  | Board paper 12/02; ToR draft v1.2
Risk | R-LEG-02 | Legislative uncertainty affects SDS scope/timeline | Pending regulations; need change-control via Legislative Radar and Delta‑Update; scenario dates for options. | G | Delivery | 4 | 4 | 16 | Red | Reduce | Monthly Legislative Radar; apply Delta‑Update; maintain scenario plan | Policy Lead | 2026-03-01 | Mitigating | Stable | Draft regs due; comms needed post‑publication | 3.9 Legislative Radar / 3.8 Delta-Update |  | Policy update note 05/02
Dependency | D-EVD-03 | Joint evidence with neighbouring SPA requires MoU & shared spec | Cross‑boundary study; align spec, QA, and refresh cadence; formalise MoU. | B | Evidence | 3 | 4 | 12 | Amber |  | Draft MoU by 15/03; agree shared spec; appoint joint QA lead | Evidence Manager | 2026-03-15 | Open | Up | Funding sign‑off by both SPAs | 3.4 Evidence Commissioning |  | Email chain 01/02; draft MoU
Issue | I-SCH-04 | Local Plan timetables not aligned with SDS milestones | Conflicting committee cycles; risk of delay to draft SDS gate; need synchronised schedule. | G | Delivery | [5 empty] | Create joint schedule; agree interim decisions protocol | PMO | 2026-02-28 | Open | Stable | All districts to confirm dates | 3.2 Initiation Pack / 3.3 ToR |  | Calendar export 02/02