3.2 Maturity Matrix: Detailed Appendices (A-D)

Version: 1.0 (Draft for review) – 2026-01-19

Appendix A: Maturity Matrix: User Guide & Scoring Manual

Purpose: provide a consistent way to baseline capability, prioritise actions, and track improvement over time across six capability areas.

A1. Capability areas and sub‑capabilities

• Governance: Decision structures & gateways; Roles & quorum; Escalation & sign‑off; Change control

• Evidence & Data: Standards & licensing; Metadata & reproducibility; Cross‑boundary compatibility; Data refresh cadence

• Digital & Innovation: Tooling & skills; AI guardrails & audit; Openness & interoperability

• Engagement: Stakeholder mapping; Seldom‑heard outreach; Plain‑English content; Feedback capture & response

• Delivery & Resourcing: Work planning & Gantt; Resourcing & budget; Supplier management; RAID discipline

• Monitoring & IIA: Indicator set & targets; Baselines & polarity; Reporting cadence; Use in decisions

A2. Levels (1–5) generic descriptors

Level 1: Nascent: ad hoc, undocumented, reliant on individuals

Level 2: Emerging: some processes defined; inconsistent application

Level 3: Established: procedures defined and followed; basic QA in place

Level 4: Advanced: optimised processes; proactive improvement & assurance

Level 5: Leading: sector‑leading practice; shared/reusable patterns

A3. Scoring method and evidence

• Score each sub‑capability 1–5. Add short evidence (links to docs, logs, or datasets).
• Where scores differ across teams, record the lowest score and note variation.
• Use the action column to capture 1–3 concrete improvements with owners and dates.

A4. Interpreting scores & prioritising actions

• 1–2 = foundational gaps: prioritise immediate actions and support.
• 3 = stable baseline: maintain; target one improvement per quarter.
• 4–5 = exemplar: consider templating and sharing practice across partners.

A5. Review cadence & governance

Quarterly re‑score at Steering Group; present a one‑page heatmap and top five actions. Link any material changes to the Delta‑Update Register and RAID.

A6. Reporting heatmap (suggested thresholds)

Red: <3; Amber: =3; Green: >3 (or set local thresholds). Highlight areas with repeated slippage or overdue actions.

A7. Template columns (for reference)

Capability area | Sub‑capability | Level (1–5) | Evidence/notes | Priority actions | Owner | Due date | Status (RAG)

Appendix B: Master Gantt & Delivery Controls

Purpose: provide a single view of phases, dependencies, and milestones; enable predictable delivery and timely decisions.

B1. Structure & minimum data set

Task/Phase | Ref or ID | Start | Finish | Duration | Predecessors | Owner | Workstream | Milestones | % complete | RAG

B2. Dependencies & critical path

Use standard dependency types: Finish‑to‑Start (FS), Start‑to‑Start (SS), Finish‑to‑Finish (FF), Start‑to‑Finish (SF). The critical path comprises tasks with zero float; delays here move the end date.

B3. Baselining & change control

Create Baseline 0 at inception; Baseline 1 after initial mobilisation; re‑baseline only after gateway decisions. All changes go through the PID change control and the Delta‑Update Register if policy‑driven.

B4. Tolerances & RAG rules (suggested)

Time: Green ≤10% variance; Amber 10–20%; Red >20%. Cost: Green ≤5%; Amber 5–10%; Red >10%. Quality: ‘Red’ if acceptance criteria at risk. Adjust locally as needed.

B5. Progress updates & reporting cadence

Weekly: workstream updates (% complete, blockers). Fortnightly: Delivery checkpoint (RAG, mitigations). Monthly: Steering Group (decisions & re‑prioritisation).

B6. Milestones & gateways

Define clear entry/exit criteria for gateways: Issues & Options → Draft SDS → Pre‑submission → Submission → Adoption. Tie approvals to Governance ToR.

B7. Risks & interfaces

For tasks with external dependencies (e.g., utilities studies, national guidance), mirror the dependency in RAID and the Legislative/Political Tracker.

Appendix C: Benefits Profile & Realisation Plan

Purpose: articulate why the programme is valuable, how benefits will be measured and when they will be realised.

C1. Logic chain (from activity to impact)

Inputs → Activities → Outputs → Outcomes → Impacts. The SDS mainly converts shared evidence and decisions (outputs) into place‑based outcomes (e.g., affordability, access, carbon) measured by the IIA indicators.

C2. Benefits register — template columns

Benefit ID | Benefit description | Type (cash/non‑cash) | Measure/KPI | Baseline | Target | Polarity (↑/↓ good) | Data source | Realisation date | Owner | Dependencies | Risks/disbenefits | Status

C3. Measurement & data sources

Link each benefit to an indicator in the IIA set. Record frequency (quarterly/annual), data owners, and calculation notes. Where indicators are proxy‑based, document assumptions.

C4. Ownership & governance

Each benefit must have a named owner responsible for tracking, reporting, and initiating corrective actions if off‑track.

C5. Disbenefits and trade‑offs

Record anticipated disbenefits (e.g., near‑term disruption). Track mitigations and ensure trade‑offs are explicit at gateways.

C6. Realisation cadence

Quarterly progress updates; annual benefits review aligned to indicator refresh and budget cycles.

Appendix D: Stakeholder Register & Engagement Plan

Purpose: identify who needs to be involved, how, when, and with which messages; ensure inclusive participation and clear feedback loops.

D1. Stakeholder categories & examples

Internal: Members, senior officers, planning, transport, housing, environment, public health, PMO. External: LPAs, CA, utilities, national agencies, developers/landowners, transport operators, NHS, environment bodies, VCSE, academia, business groups.

D2. Mapping (power/interest) & priority

Use a power–interest grid to prioritise effort. High power/high interest: co‑design; high power/low interest: targeted briefings; low power/high interest: regular updates and opportunities to contribute; low power/low interest: monitor.

D3. Register — template columns

Category | Organisation | Contact (role) | Influence (L/M/H) | Interest (L/M/H) | Information needs | Key messages | Preferred channels | Cadence | Owner | Next action/date | Notes

D4. Seldom‑heard engagement patterns

Work with trusted intermediaries; use mobile/pop‑up sessions; provide accessible/translated materials; offer small‑group formats and digital + offline mix; close the loop with ‘you said, we did’.

D5. Accessibility & equalities checks

Ensure plain‑English materials, WCAG 2.1 AA for digital content, suitable venues, and reasonable adjustment routes. Track demographics where lawful/appropriate to evidence inclusivity.

D6. Data protection & PII handling

Record only necessary contact details; store securely; respect consent preferences; avoid publishing personal data in public outputs. For AI‑assisted drafting, follow zero‑PII guardrails.

D7. Feedback capture & response

Log themes, responses, and resulting changes. Publish periodic ‘engagement summaries’ and feed issues to RAID as needed.