SDS Political & Legislative Radar: Briefing

Version: Draft | Date: 19 Jan 2026

What’s new (Jan 2026)

NPPF consultation (closes 10 Mar 2026): proposes a stronger presumption for development within settlements; support for higher density around well‑connected rail stations (incl. in ‘grey belt’ under golden rules); a re‑structured framework separating plan‑making vs decision‑making; and standardised evidence/viability inputs.

Planning & Infrastructure Act: establishes a universal SDS system and enables Strategic Planning Boards across principal authorities (factsheets and impact assessment published Sept 2025).

English Devolution & Community Empowerment Bill: Strategic Authorities (incl. non‑mayoral FSAs) progressing; GOV.UK guidance updated Dec 2025.

Political calendar shifts

Government confirmed inaugural mayoral elections delayed to May 2028 in: Sussex & Brighton; Hampshire & the Solent; Norfolk & Suffolk; Greater Essex.

Cumbria and Cheshire & Warrington expected 2027.

What this means for SDS

Approvals: Use interim Steering Board sign‑off with transition to mayoral approval when in post.

Evidence: Commission to open standards and share cross‑boundary MOUs; prepare for Strategic Planning Board scenarios.

Outcomes: Align indicators to NPPF themes (density near stations, climate/nature, economic productivity).

Engagement: Publish an ‘election delay explainer’; keep communities updated on who decides now and later.

Risk rules (RAG)

RED: Election date unconfirmed or slip ≥12 months; reorganisation milestones unknown; SDS gateways at risk.

AMBER: ‘Minded to’ delay with shadow governance forming; proceed with interim arrangements.

GREEN: Elections confirmed within 12–18 months or robust interim governance in place.

Actions this month

Seed the Political & Legislative Tracker (A/B/C streams).

Update Governance ToR with interim→mayoral transition clauses.

Add political dependency fields to the Master Gantt for each gateway.

Log changes in the Delta‑Update Register (owner/action/due).

Sources: GOV.UK NPPF consultation (Dec 2025); GOV.UK Planning & Infrastructure Bill factsheet (Sept 2025); GOV.UK EDCEB guidance (Dec 2025); national/sector coverage on mayoral election delays (Dec 2025).