# PAS Local Plan Project Initiation Document (PID) TEMPLATE

# LOCAL PLAN PROJECT INITIATION DOCUMENT

Link to guidance

## 0. Overview

0.1 Project Title:

[Type here]

0.2 Version:

[Type here]

0.3 Date:

[Type here]

0.4 Purpose of this PID document:

[Type here, example text: This Project Initiation Document (PID) sets out the management framework and approach for delivering the Local Plan. It provides clarity on the plan's scope, governance arrangements, resources, and timelines. The PID is designed as a reference tool for the team, stakeholders, and council leaders, supporting effective decision-making and ensuring everyone involved understands their roles and responsibilities throughout the plan-making process.]

## 1. Plan Scope

1.1 Role of Plan

[Type here, example text.  As a local planning authority (LPA), we have a statutory duty under both the Planning and Compulsory Purchase Act 2004 and amendments made by the Levelling Up and Regeneration Act 2023 to prepare and adopt a Local Plan. Our Local Plan establishes how land within our area will be used and developed, setting out priorities for housing, employment, infrastructure, design, and environmental standards. In planning for housing, the government’s Standard Method provides the initial benchmark for determining local housing need. Importantly, our policies must contribute to climate change mitigation and adaptation, avoid inconsistency with national development management policies, and align generally with any operative spatial development strategy relevant to our area. The Act empowers the Secretary of State to specify matters our plan must or may address. Once adopted, our Local Plan will serve as the principal basis for making planning decisions, directly shaping the future growth, development, and sustainability of our communities]

1.2 Summary of Plan Scope:

[Type here, for example is this plan updating or replacing an existing plan, are there particular policy or topic areas of focus or addition that the plan is seeking to address.]

1.3 Relationship to other relevant plans and programmes at the regional or local level:

[Type here]

## 2. Plan Timeline

2.1 Plan Stage:

☐Before notice to commence Plan Making

☐Notice to Commence Plan Making

☐ Gateway 1

☐Vision and Strategy Development

☐Gateway 2/ Draft Plan Preparation

☐Gateway 3/Confirm legal compliance

☐ Examination to confirm soundness

2.2 Plan Summary Timeline

| Ref | Activity | Indicative Start: Month/ Year | Indicative End: Month Year |
| --- | --- | --- | --- |
|  | Developing project management process and structure, governance risk register and ensuring resources are in place to begin the project (including completion of this PID) |  |  |
|  | Scoping, collating and procuring early evidence and scoping strategic environmental assessment |  |  |
|  | Scoping and production of an engagement strategy/Councillor and key internal and external stakeholder briefings/ early engagement about forthcoming plan production |  |  |
|  | (Statutory) Notice of intention to start plan making |  |  |
|  | Call for sites and initial site assessment process |  |  |
|  | Procuring Strategic Environmental Assessment |  |  |
|  | Gateway 1 (Self-Assessment)/Commencement of plan-making |  |  |
|  | Prepare Vision and Strategy for consultation feeding in emerging evidence |  |  |
|  | Strategic Environmental Assessment Scoping Consultation (note statutory minimums) |  |  |
|  | Public consultation on Vision and Strategy (note statutory minimums) |  |  |
|  | Development of draft plan including responding to consultation and any further evidence gathering |  |  |
|  | Councillor and key internal and external stakeholder briefings/ early engagement about next stage of plan production |  |  |
|  | Gateway 2 (PINS) |  |  |
|  | Deadline for submission of plan and supporting documents for approval |  |  |
|  | Public consultation (8 weeks) on Local Plan |  |  |
|  | Gateway 3 (PINS) |  |  |
|  | Plan Submission |  |  |
|  | Independent Examination (Indicative) |  |  |
|  | Plan adoption (Indicative) |  |  |

## 3. Governance and Decision-Making

3.1 Summary of Governance

Briefly explain the approval process for the local plan including any specific provisions at each plan stage where these vary

[Type here]

3.2 Council Lead (Portfolio Holder):

[Type here]

3.3 Local Plan Sponsor (Lead Officer) and Senior officer engagement approach:

[Type here]

## 4. Staff Resource and Management

4.1 Local Plan Manager (Overall Manager of Team and Process):

Enter name, job title and whether are full time 1 FTE or part time (for example, 1FTE is 5 days and 0.5 FTE would be 2.5 days)

| Name | Job Title | FTE |
| --- | --- | --- |

4.2 Local Plan Team:

Enter job titles of the rest of the team and the Full Time Equivalent (FTE) including any project manager. Add rows as needed.

| Job Level 1 (assistant grad), 2 (planner / senior) 3 Principal/ Sub Team Leader | Post status (filled / vacant) | Job Title | FTE | Estimated % time in a 12-month period on Local Plan |
| --- | --- | --- | --- | --- |

4.3 Project Manager:

| Job Level | Job Title | Dedicated PM? Y or N – other responsibilities | Internal Only Name (option to include or exclude in download) |
| --- | --- | --- | --- |

4.4 Corporate Support Needs:

| What is required | When will it be delivered | Who will deliver (Teams and Job Titles) |
| --- | --- | --- |

4.5 Identification of any additional skills requirements

List specific skills required to deliver the Local Plan that are not currently available within the Local Plan team or elsewhere in the council which may necessitate external support or specialist consultancy, such as technical evidence preparation, specialist assessments, or targeted training for staff, including any internal or external programme officers.

[Type here]

## 5. Evidence

5.1 Key Evidence

A list of key evidence needed

| Key Evidence | Area Covered (e.g. just LPA or broader) | In house, externally commissioned | Key stakeholders’ who need to input | Dependencies with other evidence documents |
| --- | --- | --- | --- | --- |
| Strategic Environmental Assessment / Environmental Outcome Report |  |  |  |  |
| Housing Needs Assessment |  |  |  |  |
| Housing Land Supply Evidence |  |  |  |  |
| Employment Needs Assessment |  |  |  |  |
| Strategic Flood Risk Assessment |  |  |  |  |
| Transport Assessment |  |  |  |  |
| Site (Selection) Assessment |  |  |  |  |
| Infrastructure Planning Evidence |  |  |  |  |
| Whole Plan Viability Report |  |  |  |  |
| Gypsy and Traveller and Travelling Show People Assessment |  |  |  |  |
| [Modify or add rows as required …] |  |  |  |  |

## 6. Stakeholder Engagement

6.1 Engagement Approach:

[Type here]

## 7. Budget Overview

7.1 Cost Estimates:

|  | Period YR 1 | Period YR 2 | Period YR 3 | Period YR 4 | Total |
| --- | --- | --- | --- | --- | --- |
| Staff |  |  |  |  |  |
| Evidence/ Consultancy costs |  |  |  |  |  |
| Engagement and consultation |  |  |  |  |  |
| Examination (PINS costs and programme officer) |  |  |  |  |  |

[Type any explanatory notes to the table above here]

7.2 Budget Reviews:

[Type here]

## 8. Risks and Mitigation

8.1 Summary of Key Risks Identified:

| Risk | Likelihood – high, medium, low | Risk level – high, medium and low | Mitigation |
| --- | --- | --- | --- |
| Add rows as needed |  |  |  |

## 9.  Approval of this PID

| Author Name: | Title |  |
| --- | --- | --- |
| Approver Name: | Title | Date Approved (attach email confirmation) |
|  | [Political lead] |  |
|  | [Chief Exec] |  |
|  | [Sponsor] |  |

## 10. Version Control/ Change Log

| Date of change (Specifying version) | Author | Reason | Updated Version Title |
| --- | --- | --- | --- |

# Guidance

## What is a PAS Local Plan PID?

To support local authorities, PAS has developed practical tools to help structure your early preparations and adapt effectively as more information becomes available. We have designed, in collaboration with MHCLG, a Project Initiation Document (PID) with the intention of testing and refining it to ultimately support the Create and Update a Local Plan resource. If you have any suggestions for improvements, then let us know at pas@local.gov.uk

The Local Plan Project Initiation Document (PID) is a practical management tool designed to support the successful delivery of the Local Plan. It helps you define and communicate the plan’s scope, governance, and resource needs while ensuring readiness for each stage of plan-making. It covers the following main dimensions of plan making:

| Topic | Detail |
| --- | --- |
| Overview | Explains the role of the PID |
| Plan Scope | Explains legal status of the plan, its scope and objectives and links to other strategies |
| Timeline | Provides an overview of the project schedule and key milestones. |
| Governance | Explains how the plan (and stages of it) are decided on an approved |
| Engagement | Identifies key stakeholder, and briefly describes the engagement approach |
| Management and resources | Identifies a project sponsor, officers responsible for project management, staff resource – and any gaps in the latter. This also identifies core team resource (positions and time allocated to plan making activity), corporate resources and any gaps which might give rise to external support needs |
| Evidence | Identifies a list of core evidence needed and at a high-level interaction |
| Budget | Budget over 3-4 years broken down by staff, evidence, including independent examination cost |
| Risk management | Headline risks and mitigation and description of risk management process |
| Approvals | Sign off from your councils’ leaders |
| Version | A log of changes/ updates to a PID |

It is up to you whether to publish your Local Plan PID in full or in part – it has been designed primarily for use internally and with key stakeholders. Sharing the most relevant sections of it beyond your core team can have significant value. It can serve as a useful tool for discussions with colleagues and key stakeholders, supporting transparency and collaboration, and ensuring your engagement approaches are well-informed and effective.

## Who should prepare a Local Plan PID?

The PID is designed to be completed by the Local Plan or Planning Policy Manager in a local planning authority with responsibility for delivering a Local Plan. Successful completion will depend on contributions from others – not least your councillor with responsibility for the plan (the portfolio holder). It's a practical way to map out your plan-making process.

## When should you prepare this PID?

Ideally, the PID should be prepared as early as possible at the very start of the process and where required updated at each key stage of plan-making or when significant changes occur:

Notice of Plan Making: Scoping and early participation.

Vision and Strategy Development.

Draft Plan Preparation.

Examination to confirm legal compliance and soundness.

Treating the PID as a live document gives you the flexibility to respond to changes as the process evolves, whether those changes stem from new evidence, engagement insights, or emerging risks. Refining and updating it at each stage ensures it stays relevant and helps you focus on the priorities for that phase – whether that's stakeholder engagement during scoping or tackling risks ahead of publishing the draft plan.

## Do I need have to prepare a Local Plan PID or use this template?

This template is designed to support plan-making activity from the initiation—or "kick-off" stage—through a structured process for planning your plan making project. Specifically, it provides a framework to help you:

- Think through the key issues you need to address to deliver the plan effectively.

Justify and secure resources and inputs from your organisation by gaining the buy-in and support of your officer and councillor leadership team, without overwhelming them with technical detail.

Clarify your plan-making objectives to key stakeholders, such as statutory consultees and infrastructure providers, by explaining what inputs you need from them and when—helping them plan.

Proactively manage risks that could derail or delay your plan.

Align your core team—including newer team members and any consultants—by providing a clear picture of what you are all working towards.

It is also your decision whether to use this PID and if there is a corporate PID template you might want to use that instead or in addition to this PID

## Where does the Plan Making PID fit in with other documents I need to prepare?

There are requirements set by the Government to publish certain, high level, information about the local plan and how and when you will consult including a requirement as set out in the Levelling-up and Regeneration Act 2023 introducing a requirement for a Local Plan Timetable..

Local Plan teams usually have a variety of tools to keep projects running smoothly. These include:

- Project Plan: Capturing your key workstreams—like engagement activities, drafting, and evidence collection (which might have its own tracker)—along with any dependencies.

Resource Plan: Allocating workstreams and tasks to team members, ensuring everyone knows their roles and responsibilities.

Consultation and Engagement Plan: Outlining how you'll communicate and collaborate with stakeholders, fostering strong relationships.

Risk Register: Highlighting key risks and detailing mitigation measures to address them proactively.

Budget: Tracking spending on the Local Plan, from staff costs to evidence gathering, to keep finances in check.

The Plan-Making PID acts as a bridge between the high-level government requirements for published information and these detailed tools. It provides a quick reference guide that clearly explains how you intend to deliver on your public commitments. This way, users within and beyond the council can understand the big picture without getting bogged down in the day-to-day details that keep the core plan-making team on track.

## How do I complete the Plan Making PID?

Here is a step-by-step guide to completing each section of the PID

### 0. Overview

#### 0.4 Purpose of this PID

What to do in the PID template: Explain the purpose of the PID in enabling plan-making – why you have produced it and how you intend to use it. We have included some standard text for you, feel free to modify it.

Why: Establishes the role of the PID.

### 1. Plan Scope

#### 1.1 Role of Plan

What to do in the PID template: State the plan’s legal role in decision making on planning applications. We have included some standard text but again feel free to amend it.

Why: This immediately clarifies the local plan role which is essential for stakeholders who may be less familiar with its legal and policy context.

#### 1.2 Plan Scope

What to do in the PID template: Define the Local Plan’s key objectives, thematic focus, and geographical scope. This is not the place to write the plan or its vision—that is the role of the Local Plan itself—but to establish the key parameters it will need to address. Identify major corporate priorities, such as affordable housing delivery, infrastructure, or sustainability goals, and clarify the geographical coverage, including likely any specific focus areas subject to assessments such as, urban centres, growth corridors.

Why: Defining the scope at the outset ensures your plan is aligned with statutory requirements, corporate priorities, and known local needs; for example, outlining a target of delivering 10,000 homes, contributing X toward achieving net-zero emissions by a certain date or tackling affordability. This alignment provides clarity for the team, leadership, and stakeholders on what the plan must achieve and avoids unrealistic expectations about what the plan can achieve.

#### 1.3 Relationship to other relevant plans and programmes

What to do in the PID template: Briefly summarise how the Local Plan needs to align with key frameworks. Here you should Identify how the Local Plan must conform with existing or emerging  strategies, such as Spatial Development Plans, wider than local transport strategies or other corporate programmes and strategies. Some of this analysis will form part of your Strategic Environment Assessment – draw on this but keep it short.

Why: Providing this summary sets the context for stakeholders or newer team members and consultants who may be less familiar with the legal and policy framework governing Local Plans. It ensures everyone understands the need for compliance with statutory requirements and alignment with national and regional policy objectives, which are essential for ensuring the plan’s soundness as well as specific pieces of work that will be required in the new system - in particular the requirement to prepare a vision which considers wider corporate strategies.

### 2. Plan Timeline

#### 2.1 Plan Stage

What to do in the PID template: Identify the current plan-making phase (e.g. Scoping, Draft Plan, Submission for Examination) and provide anticipated timelines for each stage. [This has been designed primarily as a tool for the new plan making system, but if you are using this PID under the current plan system replace the notification stage with scoping on the Sustainability Appraisal and identify Regulation 18 and 19 stages of consultation]

Why: Summarising the phases and timelines in the PID clarifies the structure of the plan-making process. While this information is included in the Local Plan timetable required under the Levelling Up and Regeneration Act 2023, having it here ensures quick and easy reference, particularly for users less familiar with the process.

#### 2.2 Plan timeline

What to do in the PID template: Provide a high-level summary of key milestones and workstreams. This should reflect the 30-month timetable for plan preparation. It is likely to go beyond the published timeline, but we encourage you to keep high-level. The main stages are included but you can add in lines for any critical activities that you think need to be covered. But again, the detail project plan used by the team rather a simplified timeline through the main stages – too much detail will make it unwieldy. [This has been designed primarily as a tool for the new plan making system, but if you are using this PID under the PCPA system overwrite the stages with scoping on the Sustainability Appraisal and identify Regulation 18 and 19 stages of consultation].

Why: Including a summary of the project timeline provides leadership with a clear, concise view of what needs to be delivered and when. It allows decision-makers to quickly understand the overall progress and priorities without delving into detailed operational plans. This summary helps maintain strategic oversight, ensures resources are aligned with key tasks, and flags potential risks or bottlenecks early on.

### 3. Governance and Decision-Making

#### 3.1 Summary of Governance

What to do in the PID template: Provide a clear description of the governance structures and decision-making points for the Local Plan process. Include details such as the role of the portfolio holder, senior officer board, and any committees involved in reviews or approvals. Highlight key stages requiring sign-off, for example: "Portfolio holder and senior officer board review prior to Cabinet sign-off at Stage [X]." Specify how these governance steps align with Gateway milestones (e.g. Gateway 2: Draft Plan sign-off). If there is an established cross-party sounding board or working group, describe their role here.

Why: A clear summary of governance structures ensures that roles, responsibilities, and decision-making processes are well understood by all stakeholders. It provides a shared understanding of the approval process at key stages, enabling democratic services officers to schedule meetings effectively and ensuring approvals/ sign offs are efficient, timely, and legally compliant. This clarity helps avoid delays, minimises the risk of missed deadlines, identifies where streamlined governance arrangements might be needed and maintains confidence in the governance framework underpinning the Local Plan

#### 3.2 Council Lead (Portfolio Holder)

What to do in the PID template: Name the councillor responsible for leading the Local Plan.

Why: This ensures clear political accountability by designating a recognised figure who can champion the Local Plan within the council and the community. Their role is essential for maintaining alignment with corporate priorities, providing leadership on key decisions, and fostering trust and transparency with stakeholders. A Local Plan needs a visible advocate who can effectively communicate its objectives, address political challenges, and ensure the plan has the necessary support to progress through formal approval stages.

#### 3.3 Sponsor (Lead Officer) and details of any Senior Officer Board/ Engagement

What to do in the PID template: Name the senior officer responsible for securing resources, providing senior oversight, and ensuring delivery capacity at both the corporate and team levels. If applicable, include details of any Senior Officer Board or engagement mechanisms that support the sponsor in aligning organisational priorities with the Local Plan’s objectives. For joint plans this might be two officer and may include a cross-boundary board.

Why: Naming the senior officer ensures clear accountability for aligning resources, resolving high-level issues, and maintaining strategic focus. This role is vital for securing buy-in at the corporate level, ensuring the plan-making team has the capacity to deliver, and leveraging support and resources from the wider organisation. Additionally, their senior position ensures they have the authority and influence to engage effectively with executive leadership, facilitating collaboration across departments. Where a Senior Officer Board is in place, it creates a forum for collective problem-solving and helps align the Local Plan’s delivery with broader organisational priorities, offering a structured way to resolve tensions between corporate programmes and ensure progress at key stages.

### 4. Project Management and Staff

#### 4.1 Leader/Manager

What to do in the PID template: Name the manager responsible for the operational delivery of the Local Plan under the direction of the project sponsor. This individual oversees the daily coordination of activities, ensuring the team works efficiently towards meeting project milestones, and manages the resources necessary to keep the plan-making process on track.

Why: Naming the Local Plan manager provides clarity on who holds responsibility for driving day-to-day progress. This role is critical for ensuring that resources—whether time, staff, or budget—are allocated and managed effectively to meet deadlines and maintain momentum. This manager acts as the central point of contact for the team, consultants, and other contributors, bridging strategic oversight from the sponsor with the practicalities of delivery.

#### 4.2 Team

What to do in the PID template: Identify posts within the team with responsibility for delivering the Local Plan. This should include job titles along with whether they are full time or part time. For internal purposes (you might want names against these). It’s important to capture the team members and time they will spend on the plan as distinct from other policy work. A rough estimate is fine – think about over a 12-month period how much time an officer will spend on tasks that do not contribute to the preparation of a local plan. For example, if someone spends 90% of their time on neighbourhood plans or other documents/ projects only tenuously related to the plan, while they are a post within the team their contribution to Local Plan development itself will be low. Get a proper handle on the level of team resource so you resource planning – including allocation of tasks to officers – is realistic and takes account or the actual capacity of these officers

Why: To realistically plan resources and workload, accurately allocate tasks, avoid delays, and manage risks effectively, it's essential to clearly understand each team member’s actual capacity and availability specifically for Local Plan activities. This ensures you are setting achievable milestones, identifying resource gaps early, and appropriately allocating responsibilities by making full use of all available capacity, ensuring all team members are actively engaged, including being part of PAS officer networks, such as the BNG and Local Plan Leaders Networks.

#### 4.3 Project Manager:

What to do in the PID template: If applicable, enter the name and role of the officer responsible for managing project-specific responsibilities in collaboration with the Local Plan Manager. This individual typically focuses on the logistical and operational aspects of plan-making, such as tracking timelines, coordinating across workstreams, and ensuring evidence preparation stays on schedule.

Why: While not every authority will do this, appointing a dedicated Project Manager or identifying senior officers in the team to focus on this can bring significant benefits. It provides clarity on who is accountable for detailed project management, including the coordination of evidence timelines, risk tracking, and workstream dependencies. This can, free up the Local Plan Manager to focus on management and complex issues.

#### 4.4 Corporate Support

What to do in the PID template: Your core plan making team will need to be supported by officers from other departments who will have a significant role developing the plan – this might be legal, environmental health, regen or other departments. You need to know who these people are – they need to know too! Capture this in this section of the PID. Think about what you need from them and when you will need it so you can communicate and, with the help of your Project Sponsor, secure the necessary Resource

#### 4.5 External Support Needs

What to do in the PID template: Having identified the team and wider corporate team that will contribute think about where there are gaps in the skills you need to complete the plan. Identify the external support or training you will need and when you will need it.  For example, you may need GIS expertise for spatial analysis, public engagement facilitation skills, or viability assessment experience. Training needs might include upskilling in viability modelling for economic assessments or using digital tools for consultations. External resources could involve engaging consultants for specific studies, such as transport assessments or Habitat Regulations Assessments (HRA) and will be reflected in Part 5.

Why: Ensuring the team has the necessary capacity and capability to deliver the Local Plan is crucial for its success. Identifying skills or resource gaps early allows you to address them proactively, whether through training, recruitment, or external support. This approach minimises delays, ensures the team is well-equipped for key tasks including those specific to the stage of plan-making

### 5. Evidence

#### 5.1 Core Evidence Required

What to do in the PID template: Identify your evidence needs – and any interdependencies, including the timeline for completion of each reflecting on the main stage, the lead officer responsible, and whether the work will be undertaken in-house or commissioned externally. Specify which stakeholder groups or organisations need to provide input for each piece of evidence and at what stage. For example, the Infrastructure Delivery Plan may need contributions from utility companies and transport authorities. Use the template to list required studies, responsible contacts, and stakeholder inputs systematically.

Why: Capturing evidence requirements clearly and early ensures you have the right resources in house or can commission support and that these requirements are included in the work plan and any briefs for consultants. This helps align timelines, responsibilities, and stakeholder engagement activities, avoiding delays or gaps in the evidence base. Additionally, it ensures your stakeholder engagement plan is tailored to secure critical inputs, reducing the risk of omissions that could affect the Local Plan’s soundness or compliance.

### 6. Stakeholder Engagement

#### 6.1 Engagement Approach

What to do in the PID template: Provide a brief summary of your overall engagement approach, focusing on key milestones and methods for engaging stakeholders. If you already have an engagement plan published you could simply include a hyperlink or summarise it.

Clearly and succinctly identify the main stakeholder groups and specify the key inputs needed from each – and at what plan stage you will be seeking this. You will need to consider the main stakeholder groups necessary for joint working/cross-boundary working including specific engagement with neighbouring local planning authorities. This is likely to help navigate where neighbouring local planning authorities will have their own plans at various stages and you will need to establish effective co-operation. Ward Member Engagement can be included in this section. Confirm that you have a councillor engagement approach in place and include a brief summary of its key elements or engagement points. This might include workshops to discuss spatial options and policy development at specific stages, materials to support councillors in communicating with their communities, and regular briefings to keep members informed and aligned.

Your approach should include appropriate engagement methods for each stage of the plan-making process, ensuring time is used effectively. It's important to design a strategy that fosters representative engagement. Beyond considering demographic factors like age and ethnicity, think about other groups who may be underrepresented in formal consultations. This could include home renters, individuals on the housing waiting list, unemployed residents, or small-scale developers. Ensuring these voices are heard can enrich the process and lead to a more inclusive plan.

You may wish highlight formal milestones like the first consultation on spatial options or informal sessions such as targeted workshops with statutory consultees during the scoping stage. But remember, this is a high-level summary, not a detailed consultation and engagement plan, which can provide more specific information about your approach to engagement.  [This PID has been designed a tool for plan making in the new system, but if you using it in the PCPA system, remember the need to comply with your Statement of Community Involvement]

Why: Summarising the engagement approach in the PID keeps it accessible and manageable while ensuring that leadership and key stakeholders have the clarity they need helping to build consensus and confidence in the approach among those involved in the plan-making process.  Engaging statutory consultees and other key groups at the right time ensures their input supports timely and informed decision-making. Effective councillor engagement ensures ward members are actively involved throughout the process, fostering transparency and collaboration. A well-structured approach helps build cross-party buy-in, smoothing the path to adoption by addressing concerns early, aligning priorities, and creating advocates for the Local Plan within the council and the community.

### 7. Budget

#### 7.1 High-Level Cost Estimates

What to do in the PID template: Provide estimated costs for staffing, evidence, engagement, and examination. Break these down by relevant periods (e.g., quarters or financial years) and include a total for each category.

Key cost areas to consider include:

Staff: Salaries or time allocations for internal team members working on plan-making.

Evidence/Consultancy Costs: Fees for commissioning studies such as transport assessments or viability appraisals or support with aspect of plan production if no in house capacity exists based on your assessment of external support needs in Section 4.

Engagement: Costs for consultation events, surveys, or digital tools to support stakeholder participation.

Examination: Projected expenses for Planning Inspectorate (PINS) fees, Programme Officer support, room bookings, audio visual equipment and other examination-related costs.

You may also want to include some notes to explain the costs identified under the table.

Why: Estimating costs ensures that adequate resources are secured and allocated appropriately. A clear understanding of financial requirements helps the leadership team prioritise funding and reduces the risk of delays due to budgetary shortfalls. Including a breakdown by period also aids in financial planning and monitoring, allowing for adjustments if actual costs differ from initial estimates.

#### 7.2 Budget Reviews

What to do in the PID template: Describe the process for reviewing and approving changes to the budget during the Local Plan’s preparation. Include details of who will oversee these changes, what triggers a review, and how approvals are formalised. Examples, of triggers for review might include significant changes to project scope (e.g., additional evidence studies required).

Identify strategies to address the key risks summarised in the PID. For each risk, outline clear and actionable measures to reduce its likelihood or minimise its impact. These strategies could include securing alternative resources, adjusting timelines, or enhancing communication with stakeholders (and you need to make sure other sections of the PID reflect this where relevant).

Why: A clear mechanism ensures that any adjustments to funding are managed transparently, efficiently, and in a way that minimises disruption to project delivery. This is critical for maintaining control over costs while adapting to unforeseen changes.

### 8. Risks and Mitigation

#### 8.1 Key Risks Identified

What to do in the PID template: Provide a summary of the main risks to project delivery, drawing on your detailed risk register. Focus on high-level risks that could impact critical milestones, soundness, or compliance. Examples include delays in obtaining key evidence, funding uncertainties for infrastructure, capacity challenges, or unexpected legislative changes. Clearly describe each risk and its potential impact, ensuring it reflects the most pressing issues identified any more detailed assessment/ detailed risk register. Your risk assessment might want to highlight significant dependencies, such as the timing of evidence studies or level of responses at the public consultation phases, to ensure the plan stays on track.

Why: Summarising the main risks in the PID keeps the document accessible while ensuring leadership and stakeholders remain aware of critical challenges.  Mitigation strategies are essential for managing uncertainties and maintaining control over the Local Plan process. By proactively addressing risks, you can reduce their likelihood, minimise their impact, and prevent delays or disruptions to the plan-making timeline. Effective mitigation helps ensure that the plan remains deliverable and has a role in maintaining corporate and stakeholder buy-in.

#### 8.2 Risk Monitoring and Review

What to do in the PID template: Confirm the process for tracking and reviewing risks throughout the Local Plan process. Specify how and when risks will be discussed, such as through regular updates at Sponsor or Senior Officer Board meetings, and where relevant, with the portfolio holder. Include details of how risks will be recorded (e.g., in a risk register) and escalated if they require higher-level intervention. Ensure the process is clearly aligned with the project’s governance framework and milestones identified elsewhere in the PID.

Why: Proactively monitoring and reviewing risks ensures that potential issues are identified and addressed before they escalate. Regular review allows risks to be reassessed as the project progresses, ensuring mitigation measures remain effective and relevant. A structured review process fosters accountability, keeps leadership informed, and provides a mechanism for timely intervention, reducing the likelihood of delays or unforeseen challenges derailing the plan.

### 9. Approval of this PID

#### 9.1 Authors and Approvers

What to do in the PID template: List the contributors responsible for preparing the PID, including their roles and contact information for follow-ups. Clearly identify those who have signed off on the PID, typically including the Lead Member, Chief Executive, and Project Sponsor. Ensure their approvals reflect a shared commitment to the proposed approach and demonstrate alignment with corporate priorities. For clarity, refer to the responsibilities of the Project Sponsor outlined under 3.3.

Why: Documenting authorship and securing formal sign-off ensures clear accountability for the PID’s preparation and approval. It facilitates follow-ups by providing contact points and demonstrates that key leaders, including councillors and senior officers, support a shared corporate vision for how the Local Plan should be managed. This alignment strengthens buy-in across the organisation and provides confidence to stakeholders that the plan is a collective priority.

### 10. Version Control

#### 10.1 Version

What to do in the PID template: Use a version control, for example, v1.0 for the first draft. Enter the date this version was finalised.

Why: Tracking versions ensures clarity and avoids confusion in communications. It ensures all users are working with the most current document.

## ACKNOWLEDGEMENTS

The guidance draws on the experiences of plan-making teams who generously shared their expertise to help us develop the Local Plan PID template and guidance.